## Sheet1
WBS Code | Work Package | Phase | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC)
1.1 | Site Clearance & Demolition | Preparation | 450000 | 450000 | 480000
1.2 | Utility Diversion (Gas & Water) | Preparation | 850000 | 800000 | 920000
2.1 | Bulk Earthworks & Excavation | Groundworks | 1200000 | 1100000 | 1050000
2.2 | Piling & Retaining Walls | Groundworks | 2100000 | 1800000 | 1950000
3.1 | Reinforced Concrete Substructure | Structural | 3400000 | 2550000 | 2800000
3.2 | Structural Steel Framing | Structural | 1500000 | 450000 | 420000
4.1 | Drainage & Surface Runoff Systems | Civil Works | 750000 | 600000 | 580000
4.2 | Road Sub-base & Paving | Civil Works | 950000 | 190000 | 210000
5.1 | Snagging & Final Inspection | Handover | 300000 | 0 | 0